## Issues Log
Function | Date Found | Description | Status/Notes | Workaround
Blog - Blog Posts | 2014-01-09 | I can't attach a blog to an actual page. I can preview a post. I can preview what the blog page will be, but I can't put them together on the sandbox site.
Blog - Blog Posts | 2014-01-03 | Blog posts show title of post twice. Can we remove the second title appearing in the post?
Blog - Blog Posts | 2013-12-20 | Application error if you do not add an image to the image field.
Blog - Blog Posts | 2013-12-17 | Images uploaded separately from the post creation. | Joel is still thinking about this
Blog - Carousel | 2014-01-08 | To be able to add a carousel (one that looks like the one on the homepage) anywhere on the library website.
Blog - News and Announcements | 2013-12-17 | Be able to change order of the promotions every few days | Joel will create an interface that will allow this
Blog - News and Announcements | 2013-12-17 | when we click on each of the posts on the carousel it can link to a page. | Discussed with Joel; the image will be the link You will also notice that there is a wysiwig editor. This is to create a page of content that is linked too. Joel can reuse the URLRedirect form field from pages to allow me to make it so it links to external sites.
Blog - News and Announcements | 2013-12-17 | In the News and Announcements blog can it change to the next item in the carousel every 8 seconds.
Blog - News and Announcements | 2013-12-17 | When I tried adding an event to this blog I saw a new post was added indicated by a number, but I would not be able to see the actual post. When I click on the number for the new post the number disappears. The number would reappear again when I press the number for the second post. If I press the number for the second post again it disappears.
Blog - News and Announcements | 2013-12-10 | "View All News" isn't built out
Blog - Posts | 2013-12-17 | I was creating a random blog post. It was not for the News and Announcements block on the homepage. It was just for anything and it gave me an application error because I did not have an image. Is it necessary to have to always have an image when we make a blog post?
Blog - Posts | 2013-12-11 | Only staff to post to the blog. Comments are open to the public of course. Comments to be auto approved; Content authors can delete any comments that are inappropriate afterwards. Content authors to be able to fix grammatical errors that the staff who are not content editors post, Content authors to be able to delete a post altogether if need be. I want posts to only live for a year then go away. The email addresses of the content authors are Mark Flowers maflowers@solanocounty.com and Kevin Tolley kmtolley@solanocounty.com Can these be easily changed by me if any of these people quit?
Blog - Press Releases | 2013-12-09 | Would like to keep press releases for one year before it expires or disapears
Blog - Share Capablities | 2013-12-11 | Put the share feature on the dedicated blog post page. Have the word “Comment” be changed to “Comment/Share” | "Comment/Share" has been added
Blog - Teen Blog | 2013-12-20 | On the current site there is a Subscribe to our RSS Feed link on the teen blog. Is it still possible to have a RSSS feed?
Calendar - Create an Event | 2014-01-09 | Add recurrence option
Calendar - Create an Event | 2014-01-09 | Created a test event where the beginning date was the same day as the end date and it gave an application error. | See screenshot from document CMS-ScreenshotofIssues-2014-Jan9.doc
Calendar - Create an Event | 2014-01-03 | If I fail to add a required field can we make it so that the system does not erase fields I already filled in.
Calendar - Create an Event | 2013-12-27 | Make "End Date" field a non-required field? We only have one event that lasts more than a day.
Calendar - Create an Event | 2013-12-27 | Can we add "All Branches" to the Branch field in the "Create an Event" form
Calendar - Create an Event | 2013-12-27 | Events not showing up in the Featured Events box
Calendar - Create an Event | 2013-12-27 | When I choose to not add an end time it automatically puts in the beginning time as the end time for an event. Can we make it so that no end time appears if we choose not to put in an end time?
Calendar - Create an Event | 2013-12-27 | When I add an event for a future month it reverts back to the current month after I finish editing. Can we make it so that it stays on the month that I am working with, so that if I need to go back and edit I do not have to toggle through the months again?
Calendar - Create an Event | 2013-12-17 | Adding an event form in the Extensions/Calendar – The save button at the top of the form does not work. This button is there after you have already created the event and have decided to go back in to edit.
CMS Function | 2014-01-09 | Ability to cancel out of any place without saving and it exits the page you were trying to edit and take you back to the previous page without having to go through the directory of page, posts, events, etc
CMS Function | 2014-01-09 | Add a way to see history of edits to a created page, post, etc that will allow you to go back to previous versions
CMS Function | 2013-12-17 | Sometimes when I miss a field and the CMS tells me which required field to fill, it erases or resets another field to default
CMS Function | 2013-12-11 | Preview mode does not show what the page would really look like on the website | Not functioning because of future enhancement | Go to the sandbox site
CMS Function | 2013-12-11 | I created a page to be added to the Catalog Links and it did not show up. The page is a form if that makes any difference | Currently nothing is fielding to those teal boxes (1/3)
CMS Function | 2013-12-03 | Ability to save periodically
Content Editor - Attachments | 2014-01-09 | Unable to attach a document from the document repository as a link in the text
Content Editor - Block Quote Function | 2014-01-03 | Block quote button shows no effect but the correct code appears in source mode.
Content Editor - Bold Function | 2013-12-27 | Bold function and <strong> tag does not work |  | use <span class="fiction"> to imitate
Content Editor - Embed | 2013-10-11 | The ability to embed youtube video | COMPLETED - I had forgetten that I had already tested this
Content Editor - Italic function | 2014-01-03 | Italic button shows displays no effect in the editor. Code is source mode is added correctly.
Content Editor - Link | 2014-01-09 | Add field for tool tip for accessibility purposes. I have seen this in other places and did not know if it is something we need to have.
Content Editor - Link Properties | 2013-12-20 | Add the link type for email | COMPLETED
Content Editor - Ordered Lists | 2013-12-11 | Ordered Lists button displays no effect in the editor; however the code is added in source mode.
Content Editor - Paragraph Format Function | 2014-01-03 | When creating text in preformatted text there is no effect. The correct code is displayed in source mode.
Content Editor - Paragraph Format Function | 2014-01-03 | When creating text in heading 1 in the content editor the text turns yellow. The correct code diplays in source mode.
Content Editor - Paragraph Format Function | 2013-12-11 | When creating text in heading 3 in the content editor the text turns white and disapears from view. The text size does grow and the code is correctly stated in source mode
Content Editor - Paragraph Format Function | 2013-12-11 | When creating text in heading 2 in the content editor it displays no effect in the editor other than changing the text to black rather than gray. The correct code displays in source mode.
Content Editor - Paste as Plain Text | 2013-12-03 | Paste as plain text does not clear formatting of brought over formats
Content Editor -Styles-Inline Styles | 2014-01-03 | The Following inline styles have no effect but shows within the source view: Marker, Big, Small, Typewriter, Computer Code, Keyboard phrase, Sample text, Variable, Cited Work, Inline Quotation, Language: RTL, Language: LTR
Content Editor - Tables | 2014-01-03 | Tables will not appear in the visual mode but code shows in the source mode
Content Editor - Unordered Lists | 2013-12-11 | Unordered Lists button displays no effect in the editor; however the code is added in source mode.
CSS | 2013-12-27 | When creating links on unordered lists the link color needs to be "#b74942"
FAQ | 2013-12-11 | In the published version it does not work like a FAQ where you click on the question and the answer slides down
FAQ - Ordering | 2014-01-03 | When I tried to change my items into a different order it worked once and then it just stopped working.
Form - Book News page | 2013-12-18 | I just don’t know what to do about, how to create a page for or what we can do about with the new cms. It’s this e-News Sign-up page. http://solanolibrary.com/signup/ The first box uses MailChimp in order for people to sign-up. The second box uses a vendor which we use called booksite and when a patron clicks sign up it goes to http://library.booksite.com/7189/signupSubscribe/?list=NLSGN . The last box happens to be the only easy one to work with. There is a bunch of code in our current CMS for getting it to work with MailChimp that it’s overwhelming. I don’t know what half of it is really for. The booksite has all a list of Genres you can check off, but the genres have a code they use as the value that identifies which newsletter to send. For example New Fiction is NLNF. Out of curiosity I pasted in the code for booksite and it did create a form in the CMS http://mjsdev.solanolibrary.com/Page/PagePreview/128 However, you have to highlight over the area where the checkboxes are in order to see the labels. Do you have any advice on what we should do about this page?
Form - Book News page | 2013-12-09 | I am going to need to have the method to post. It will need to have full width template. | Joel has says that the forms will be able to post. We have already accomplished full width template.
Form Builder | 2014-01-10 | The password field does not mask the characters with stars
Form Builder | 2014-01-10 | I tried to create a question with radio buttons, a checkbox on a form and it turned into a text field instead
Form Builder | 2014-01-10 | We have a calendar field on our current cms that did not work well with the forms, so I was never able to use it. Do you have a calendar field we can use that would work properly.
Form Builder | 2014-01-10 | Need the ability for the form to go to a success page after the patron has pressed submit
Form Builder | 2013-12-26 | To be able to add text between a form's fields. We have some forms with a disclaimer or note before the customer presses the send button | We can create a specific type of form field that will just display some text. Technically not a form field but will give you some flexibility to add text where you want.
Form Builder | 2013-12-11 | Can you add the following validation type: Library card number
Form Builder - Form Order | 2013-12-11 | After I created my form and put my form in order I could not go back in and adjust field order. Some of the fields went out of order. The arrow buttons decided to stop working so I could not put them back. I had also set the required fields using by changing the green exclamations to red but they went away.
Form Builder - Form Submissions | 2013-10-31 | Some get sent to specific librarians, three of them get sent to an Solano County Library email, one I extract the data of the form weekly. Need to be able to define who the form submissions go to each time you create a new form and need to be able to extract data. | I have sent information to Joel on how we currently extract data.
Media | 2013-10-11 | Ability to upload an Mp3
Media - Document Repository | 2013-12-10 | I gett an application error that says Maximum Request Length Exceeded. We have a collection of newsletters on our website. The issue is the file is too big but we want to still offer them on our website. |  | We can try to create web pages out of them, but we are not sure if we can replicate them as a webpage.
Media - Document Repository | 2013-10-11 | Ability to upload Word, Excel, PDF
Media - Image Gallery | 2013-12-20 | Uploaded images will not appear in the Image Gallery. It shows a title of the image but not the image. When browsing for the image while creating a page or post, there is no indication that the image has been uploaded.
Media - Image Gallery | 2013-12-12 | To have back buttons or breadcrumbs in the image gallery area
Media - Image Gallery | 2013-12-12 | I tried to delete an image that I was using in a widget. I removed the image from the widget first then deleted from the media area. When I tried to delete it from the recycle bin I was given an application error that said it was being used by another process. I checked to make sure that it was not in widget again. It was not there. Saved the widget for good measure then went back to the Recycle bin to delete. It went away without error. I had to do it a second time and I realized it takes a couple of minutes before you can actually delete an item from the recycle bin. | Issue with the images not able to delete is due to it being locked
Media - Image Gallery | 2013-12-12 | Uploaded a new modified image that had the same file name as one that I had just deleted and it retained the look of the old image. | Issue with the images not able to delete is due to it being locked
Media - Image Gallery | 2013-12-12 | Unable to overwrite image file; causes application error | Issue with the images not able to delete is due to it being locked
Media - Image Gallery | 2013-10-11 | Formats to be able to upload jpg, gif, png | So far I know that I can upload a jpg
Pages | 2014-01-09 | Ability to modify URL so that it does not just use an id number The system would automatically create the URL by using what is in the title field or perhaps even the navigation name field and it would automatically modify the text so that it does not have any spaces in the name. Creating a page under any parent page (such as Research) would automatically have the URL that will do something like this – solanolibrary.com/research/nameofnewpage
Pages | 2013-12-11 | Only select second level pages will need to show up in the teal menu box. Can you make it so that we can choose which second level page will show up in the teal menu box? Here was my original question from the email: I am trying to create a page under a category without it showing in any of the menus. You mentioned below that “pages have a field associated with each one called Navigation Name. What ever you put in this field is going to be what appears on the main menu.” I could not make a page without filling out this field. It would stop me and say I must enter Navigation Name. Say this field was not a required field and we were able to leave this field blank. Would it mean that the page would not show up in any menu? | Saw that function has been turned off (1/6)
Pages - Homepage | 2014-01-09 | Have the News and Announcements box be a set size so that does not expand and contract as you toggle between items in the carousel.
Pages - Homepage | 2013-12-02 | The section of the homepage which has a listing of links (we call it "placemat menu") I have chosen the option to have more control over it, which will require me to maintain several different menus | This may already be taken care of. I need to go in and check.
Pages - News | 2013-12-10 | We will need to have conversations on layout etc. | Joel doesn't expect I will like the simplistic layout as it stands right now.
Social Media - Share Capablities | 2013-12-09 | Needs: The social media platforms we wish to have are: Facebook, Twitter, Pinterest, “share by email” and “like this”; Is it possible to also have “save” and “print”? Use: We would use it for blog posts, book lists, pages most people use, events, and subject category pages. Question: Ann wonders if there is any possible way you can show examples embedding share links into templates? If not, can you explain where they would go. I think we would prefer embedding to the template, but we are not entirely sure what we are imagining is what you mean. | Joel can create a special widget for the side bars (containers) or I can embed the share links into templates directly
Template | 2013-12-11 | Can menus in the upper right corner of the website and in the teal boxes be made into 2 columns? | Upper right hand menu is now in 2 columns
Template - Individual Image Headers | 2013-12-17 | I went through the whole website to see which pages have personal headers. Here is the list of pages. I am hoping that I did not miss anything. Main Pages: Home, Catalog, Kids, Teens, Research, Programs, Go to the Web, Ask Us [8 total] Pages on Upper Right Menu: Library News, About the Library, Biblioteca Espanol [3 total] Pages Under Programs: Book Clubs, Read Away Fines (these two have the same header) Lawyers @ Your Library, Reading Readiness, Spanish Storytimes, Storytimes, Summer Reading, Library Buddies, The Big Blue Bin of Books, Literacy, Reach out and Read, Friends of the Library, Library Volunteers, The Library Foundation [14 total] Pages Under Hours and Locations: Fairfield Civic Center Library, Fairfield Cordelia Library, John F. Kennedy Library, Law Library, Rio Vista Library, Springstowne Library, Suisun City Library, Vacaville Cultural Center Library, Vacaville Town Square Library [9 total] 34 headers in all.
Template - Teal Menu Box | 2014-01-09 | For each of the main pages these menus should have different headings. Catalog - "Catalog Links"; Teens - "Teen Links"; Programs - "At the Library" etc.